## Timeline
Developer: |  | Avinash Yadav
Project: |  | Data Ingestion - Admin Module (RBAC) and Login Methods
Total Hours: |  | 108
Development hours/Per day: |  | 6
Development Start Date: |  | 2026-10-08
Development End Date: |  | 2026-11-02
Estimated effort: 108 hours at 6 hours/day (18 working days). Yellow tasks: scope and estimate to be confirmed.
Sno | BRD # [optional] | Task Breakdown | Team | Total FE | Start Date | End Date | Comments
1 |  | Admin Module setup Extend existing user and group details for login method, DI Group ownership, approval status and roles. | FE | 4 | 2026-10-08 | 2026-10-08
2 |  | Google Login and Google Groups Add Google sign-in and connect permitted Google Groups to application access. | FE | 10 | 2026-10-08 | 2026-10-12
3 |  | Custom Login and OTP Add signup, password change/reset and Twilio OTP. Reuse TPMailer for temporary-password emails after DI Group owner approval. | FE | 16 | 2026-10-12 | 2026-10-14
4 |  | Admin Module > DI Groups Add group registration with name, description, owner, owner email and roles. The nominated owner joins without membership approval. | FE | 10 | 2026-10-15 | 2026-10-16
5 |  | Admin Module > New User and User Approval Add user registration and membership requests for the selected DI Group owner to approve or reject. | FE | 9 | 2026-10-16 | 2026-10-20
6 |  | Standard roles and Permission (User Roles Assignments) Set up the five standard roles and their menu/action access, and allow roles to be assigned to users. | FE | 9 | 2026-10-20 | 2026-10-21
7 |  | Custom Role (Menu Permissions) Allow additional roles to be created with selected menu and action permissions. | FE
8 |  | Role-based access on existing screens Apply permissions to Dashboard, process creation/execution, Process List, Real Time Status and Processed File List, including own-created and group records. | FE | 11 | 2026-10-21 | 2026-10-23
9 |  | Region / Sub Region / Client and resource mappings Add Admin screens to maintain DI Group mappings for regions, Database, Storage Account and Databricks using existing lookups. | FE | 9 | 2026-10-23 | 2026-10-26
10 |  | Source Connect (Workspace Connect) Extend existing SharePoint and Google Drive access for the new roles and DI Groups, and show source setup-request status. | FE | 6 | 2026-10-27 | 2026-10-27
11 |  | Menu Modification and navigation Add menu/icon/naming controls. Rename Add New to Create Process, Process Configuration to Process List, and File Process Status to Real Time Status. | FE | 6 | 2026-10-28 | 2026-10-28
12 |  | Security Group selection Extend the existing selector for approved DI Groups and Google Groups, and refresh role access when the group changes. | FE | 6 | 2026-10-29 | 2026-10-29
13 |  | Reporting Module Define Utilisation reports and the required Power BI reporting views. | FE
14 |  | Unit testing and regression checks Check new login, approval and role access, confirm existing Azure login and process flows, and resolve findings. | FE | 12 | 2026-10-30 | 2026-11-02
|  | Total estimated hours |  | 108
Formulas:
Start Date = WORKDAY(C5-1,INT((SUM(E9:[Total FE, row above]))/C4)+1,C27)
End Date = WORKDAY(C5-1,ROUNDUP(SUM(E9:[Total FE])/C4,0),C27)